## Slide 1
EVENT CAMPAIGN BRIEFING

## Slide 2
AGENDA
The Set-up
01
The Event
02
03
The Lists
04
The Campaign

## Slide 3
CONSIDERATIONS FOR AN ENGAGING EVENT
  Define your target audience
  Create a topic that captures the audience
  Presentation slides, different from the Corporate Presentation?
  Invite guest speakers who add value
By taking time to conceptualize, plan and prepare we can create a unique and engaging event with increased attendance rates.

## Slide 4
CAMPAIGN PREP
CAMPAIGN APPROVAL
CAMPAIGN PROMOTION
LIVE EVENT
LIST MANAGEMENT
POST PROMOTION
CAMPAIGN
To ensure a successful event we need to
consider the complete campaign.
In the following slides you will see examples of a complete campaign.
We understand that each client is unique in their requirements so please use these as a guide to create the complete campaign.
IT’S MORE THAN THE LIVE EVENT!
CAMPAIGN PHASES
ESTIMATED TIMEFRAME: 4.5 WEEKS

## Slide 5
About/BIO | We need a compelling summary of the webinar event and list of topics that will be discussed in the webinar, along with the BIOs of the Speakers. | Account Lead
Target Audience | We need to define the Target Audience and request a quote on how long it will take to target the right investors. This will be a factor in determining the timeline of the campaign. | Account Lead
Schedule | We need to complete the schedule template, with dates, for the complete campaign. | Account Lead
Place | For a physical event, we need to determine the style of event, capacity target, and budget, this will help us find a suitable location for the event to propose to the client. | Account Lead
Assets | We would create all campaign assets prior to launching the campaign to set up automation. This is a factor in determining the timeline of the campaign. | Marketing
COMPONENTS:
THE SET UP

## Slide 6
Invites | We can design email and social posts to announce and promote the event. | Marketing
Landing Page | We can design a landing page to capture RSVPs. This landing page can be designed with a custom registration form and consent policies to gather the right information. | Marketing
Automation | Depending on the client’s email infrastructure we can review the possibility of setting up automation. Alternatively if they need this infrastructure setup, it will take 5 business day. | Marketing
List Mangement | Depending on the client’s email infrastructure we can review how best to manage RSVP’s and the communication plan. | Account Lead/Marketing
COMPONENTS:
THE SET UP
Important Question: What email infrastructure is the client using or does this need to be set up?

## Slide 7
Timeframe | We recommend 1 month + prior to the event date to promote the event. | Account Lead
Channels | We recommend promoting this on the social channels that reach the target audience, by targeted email to clients distribution list and featured in the AAIR newsletter. | Account Lead
Sponsored/Boosted Post | There is the option to “boost” the post, turning the event post into an Ad to reach more audience, if appropriate for the event. Additional spend required. | Marketing
Sponsored Partners | We have a network of partners that can help distribute the event notice, this can be through their newsletters or social channels. Possible additional spend required. | Account Lead
COMPONENTS:
PROMOTION

## Slide 8
THE LISTS
To ensure a successful event we need to
consider the target audience.
Our approach is to take run a targeting
exercise to identify investor profiles from
within our community and we will also
target new contacts. This effort is
completed by the Capital Markets team.
All”Leads” are appropriately tagged to the Client account event to support communication plans.
TARGETING AND LIST MANAGEMENT
Capital Marketing Targeting Exercise
( X Time)
Creates a new Contact List for this event promotion
Email
Call Out
PROMOTION PHASE
PREP PHASE
POST EVENT PHASE
Email

## Slide 9
Event
Landing Page
(Mailerlite)
Zoom
(if applicable)
Thank You Email
Mailchimp
COMMS PLAN
24 Hour Notice Email
Post Event Email
REGISTER
Reminder
Email 1
Reminder
Email 2
ADD DATE
ADD DATE
ADD DATE
ADD DATE
ADD DATE
Social Post
Email
Call
Campaign
News Release
Post Event Social Post

## Slide 10
Host(s) | Please determine who the host will be for this webinar. | Account Lead
Script | We need to prepare a script for the webinar that will be sent to the Client in advance. This script must include an intro, disclaimer, and pre-populated questions. | Account Lead
Timing | Average timing of the presentation is 45 min, 30 mins presenting with 15 min Q&A. Important to put in the invitation the time to arrive and the time the presentations start. | Account Lead
Interactive | (If applicable) Account Lead must be present during the event to manage questions, schedule of events and other coordination efforts with the client. | Account Lead
COMPONENTS:
THE EVENT

## Slide 11
Recording | (If applicable) The raw video will be saved in the client folder. | Marketing
Post Editing | The marketing team will edit the Long Form Video with Slide overlays. The video will be sent to the Account Lead to select the TimeStamps for where to place the overlayed slides or copy. Upon Request we can slice the presentation into Video Shorts. Please see example: https://preview.mailerlite.com/t8i5f2q2g6 Turn Around time is: 48 hours. This is a consideration for the complete campaign timeline. | Account Lead & Marketing
On Demand Video | On-Demand Video (Long or Shorts) are placed on custom event landing page | Marketing
TO CONSIDER
POST EVENT

## Slide 12
PRA COMMS | Included Email, social and custom landing page for registration and on-demand: Branded Emails (Pre, Post, On-Demand Email Example) -Branded Landing Page for Registration (Pre, Post Example) -4 Pre-Promotional Posts (2 for AAIR & 2 for client) -Turn Recording into Shorts for Post-Promotion Posts (YouTube Playlist Example)
Stardust | Included: Registration Landing page
WIMBC | Included: Branded landing page.
EXAMPLES
PAST CAMPAIGNS

## Slide 13
Case Study Stardust Power (CONFIDENTIAL) | Emails for NASDAQ Opening Bell Ceremony: Invite Reminder - to those who didn't confirm on June 28, can resend on July 2 Confirmed - Automatically Reminder to those confirmed - 3 days after confirmation (because they may confirm after June 28 or July 2, so with this delay, it ensures everyone gets the reminder email) Day before Event - July 10 Emails for CORE Club Luncheon: Invite Reminder - to those who didn't confirm on June 28 Confirmed - Automatically Reminder to those confirmed - 3 days after confirmation (because they may confirm after June 28 or July 2, so with this delay, it ensures everyone gets the reminder email) Day before Event - July 10 Heres the NASDAQ Bell Ceremony Invite Link Heres the CORE Club Luncheon Invite link Live excel sheet of confirmed people.
EXAMPLES
PAST CAMPAIGNS

## Slide 14
Event Landing Page
Thank You Page &
Email sent
Annoucement Email
CAMPAIGN OUTLINE
Reminder 1
Reminder 2
Wrap-up
Email
Wrap-up
Report
On-Demand Landing Page
01
02
03
04
05
06
07
Launch Custom Registration Landing Page
Proposed Process

## Slide 15
Proposed Process
Event
Annoucement Email
CAMPAIGN OUTLINE
Reminder 1
Wrap-up
Email
Wrap-up
Report
On-Demand Landing Page
01
02
03
04
Launch Custom Registration Landing Page

## Slide 16
NEXT STEP...
If you are ready to start planning, submit a Ticket to Marketing and let’s get going!
Submission Form - Click Here